## Scrum Burn Up Chart
SCRUM BURN UP CHART SPRINT 0
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Realizar la Toma de Requerimientos con el Cliente |  | ST | Complete | 8 | 2 | 1 | 2 | 0 | 1 | 0
Realizar el documento de Visión y Alcance |  | ST | Complete | 8 | 2 | 2 | 1 | 0 | 0 | 0
Realizar Product Backlog priorizado |  | ST | In Progress | 8 | 2 | 2 | 2 | 1 | 1 | 0
Realizar el Sprint Planning |  | CC | Complete | 4 | 2 | 1 | 1 | 0 | 0 | 0
Realizar el Sprint Backlog |  | MT | Complete | 1 | 1 | 0 | 0 | 0 | 0 | 0
Realizar la Definición de Hecho (DoD) |  | AV | Complete | 2 | 0.5 | 1 | 0.5 | 0 | 0 | 0
Realizar el Sprint Goal |  | CC | In Progress | 1 | 0.5 | 1 | 1 | 0 | 0 | 0
Realizar el Burndown Chart |  | AV | Not Started | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Realizar el Burnup Chart |  | MT | In Progress | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Realizar el Roadmap |  | ST | In Progress | 6 | 1 | 2 | 2 | 0 | 0 | 0
Realizar el Sprint review |  | ST | Not Started | 2 | 0 | 0 | 0 | 0 | 0 | 0
Realizar el Sprint Retrospective |  | ST | Not Started | 1 | 0 | 0 | 0 | 0 | 0 | 0
Realizar el Checkpoint |  | ST | Needs Review | 1 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 43 | 11.5 | 10 | 9.5 | 1 | 2 | 0

## Referencias
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold